## Party Planner
Release B and C
CLIENT |  |  |  |  | ASDA
PROJECT LEAD |  |  |  |  | Aniket & Anurag | [8 empty] | DATE & TIME |  | 2023-05-08
ADDITIONAL INFO |  |  |  |  | OMS George, Grocery, Picking Shop and IAM/CRM Interface's Details
Checklist
OMS George (Interface's) | [10 empty] | OMS Grocery (Interface's) |  |  |  |  | SHOP (Interface's)
✔ | IFDD-0022 |  | ✔ | IFDD-0032a |  |  | ✔ | IFDD-003 |  |  | ✔ | 8A |  |  |  | ✔ | G-ERDS-006
✔ | IFDD-0022a |  | ✔ | IFDD-0032b |  |  | ✔ | IFDD-18a |  |  | ✔ | OMS003
✔ | IFDD-0019 |  | ✔ | IFDD-0032c |  |  | ✖ | IFDD-1,2,48 |  |  | ✔ | 008C
✔ | IFDD-006a,b |  | ✔ | IFDD-0032d | [6 empty] | ✔ | 33
✔ | IFDD-0018 |  | ✔ | IFDD-0004 | [6 empty] | ✔ | IFDD-27
✔ | IFDD-0052 |  | ✔ | IFDD-53
Picking (Interface's) | [10 empty] | IAM AND CRM (Interface's)
✔ | Order Creation (PFO,UFO,CFO,UODS)
✔ | Event Handler (Order Event DWH, WMT ODS) | [9 empty] | ✔ | IAM
✔ | MDM(Store Layout, Item Volumetric) | [9 empty] | ✔ | CRM
✔ | CINE(Register Device, Check-in, Push Notification, Check-in - Event Handler)
✔ | Valid Sub-check API
✔ | Error Scenarios Alerts and Monitoring
Details
CATEGORY | [5 empty] | GEORGE |  | Grocery | Picking |  | IM/CRM
Total No. of functional Scripts | [5 empty] | 612 |  | 542 | 1084 |  | 148
Total scripts Automated | [5 empty] | 383 |  | 171 | 717 |  | 119
Percentage completion | [5 empty] | 62.5817 |  | 31.5498 | 66.1439 |  | 80.4054
Status | [5 empty] | GREEN |  | GREEN | GREEN |  | GREEN
George |  |  |  | Bugs |  |  | Comments |  |  |  | Total No. of functional Scripts |  | Total scripts Automated |  | Percentage completion |  |  | Expected End date
[11 empty] | 612 |  | 383 |  | 62.5817
IFDD-0022 | [10 empty] | 61 |  | 44 |  | 78.4615 |  |  | TO BE DECIDED
IFDD-0022a | [10 empty] | 99 |  | 95 |  | 95.9596 |  |  | TO BE DECIDED
IFDD-0019 | [10 empty] | 65 |  | 51 |  | 78.4615 |  |  | TO BE DECIDED
IFDD-006a,b | [10 empty] | 32 |  | 32 |  | 100 |  |  | TO BE DECIDED
IFDD-0018 | [10 empty] | 28 |  | 28 |  | 100 |  |  | TO BE DECIDED
IFDD-0052 | [10 empty] | 21 |  | 14 |  | 66.6667 |  |  | TO BE DECIDED
IFDD-0032a |  |  |  | 6770 |  |  | https://asdauk.atlassian.net/browse/ASDAF-6770 |  |  |  | 19 |  | 8 |  | 42.1053 |  |  | TO BE DECIDED
IFDD-0032b | [10 empty] | 25 |  | 15 |  | 60 |  |  | TO BE DECIDED
IFDD-0032c | [10 empty] | 11 |  | 8 |  | 72.7273 |  |  | TO BE DECIDED
IFDD-0032d | [10 empty] | 19 |  | 15 |  | 78.9474 |  |  | TO BE DECIDED
IFDD-0004 | [10 empty] | 57 |  | 38 |  | 66.6667 |  |  | TO BE DECIDED
IFDD-53 | [10 empty] | 21 |  | 8 |  | 38.0952 |  |  | TO BE DECIDED
IFDD-003 | [10 empty] | 43 |  | 8 |  | 18.6047 |  |  | TO BE DECIDED
IFDD-18a | [10 empty] | 24 |  | 19 |  | 0 |  |  | TO BE DECIDED
IFDD-1,2,48 |  |  |  | 5140 |  |  | https://asdauk.atlassian.net/browse/ASDAF-5140 |  |  |  | 87 |  | 0 |  | 0 |  |  | TO BE DECIDED
Grocery |  |  |  | Bugs |  |  | Comments |  |  |  | Total No. of functional Scripts |  | Total scripts Automated |  | Percentage completion |  |  | Expected End date
[11 empty] | 542 |  | 171 |  | 31.5498
8A | [10 empty] | 86 |  | 33 |  | 38.3721 |  |  | TO BE DECIDED
OMS003 | [10 empty] | 50 |  | 50 |  | 100 |  |  | TO BE DECIDED
008C | [10 empty] | 41 |  | 34 |  | 82.9268 |  |  | TO BE DECIDED
33 | [10 empty] | 64 |  | 20 |  | 31.25 |  |  | TO BE DECIDED
IFDD-27 | [10 empty] | 301 |  | 34 |  | 11.2957 |  |  | TO BE DECIDED
0
Picking |  |  |  | Bugs |  |  | Comments |  |  |  | Total No. of functional Scripts |  | Total scripts Automated |  | Percentage completion |  |  | Expected End date
[11 empty] | 1084 |  | 717 |  | 66.1439
Order Creation (PFO,UFO,CFO,UODS) | [10 empty] | 286 |  | 212 |  | 74.1259 |  |  | Completed
Event Handler (Order Event DWH, WMT ODS) | [10 empty] | 166 |  | 42 |  | 25.3012 |  |  | Completed
MDM(Store Layout, Item Volumetric) |  |  |  | ASDAF-7094 |  |  | 20 test failed today issue raised in Jira is ASDAF-7094 for MDM, which remains open |  |  |  | 35 |  | 30 |  | 85.7143 |  |  | Completed
CINE(Register Device, Check-in, Push Notification, Check-in - Event Handler) | [10 empty] | 73 |  | 7 |  | 9.589 |  |  | Completed
Valid Sub-check API | [10 empty] | 27 |  | 15 |  | 55.5556 |  |  | Completed
Error Scenarios Alerts and Monitoring | [10 empty] | 201 |  | 173 |  | 86.0697 |  |  | Completed
IAM AND CRM |  |  |  | Bugs |  |  | Comments |  |  |  | Total No. of functional Scripts |  | Total scripts Automated |  | Percentage completion |  |  | Expected End date
[11 empty] | 148 |  | 119 |  | 80.4054
IAM |  |  |  | ASDAC-11532 |  |  | Issue raised for single profile website |  |  |  | 45 |  | 45 |  | 100 |  |  | Completed
CRM | [10 empty] | 103 |  | 74 |  | 71.8447 |  |  | Completed
AT URL FOR TODAY’S EXECUTION:
Picking |  | https://dev.azure.com/asda-ccoe/Asda-ETS-Int/_build/results?buildId=131899&view=ms.vss-test-web.build-test-results-tab
IAM |  | https://dev.azure.com/asda-ccoe/Asda-ETS-Int/_build/results?buildId=90769&view=ms.vss-test-web.build-test-results-tab
OMS George |  | https://dev.azure.com/asda-ccoe/Asda-ETS-Int/_build/results?buildId=125459&view=ms.vss-test-web.build-test-results-tab
OMS Grocery |  | https://dev.azure.com/asda-ccoe/Asda-ETS-Int/_build/results?buildId=125996&view=ms.vss-test-web.build-test-results-tab